# SparkCity

# Team Work Plan: V1

Two Teams of Three • Full Five-Day Plan, Starting at Day 1 • Shared-Code / Shared-Database Strategy

Purpose. This plan reorganizes the six-person SparkCity team into two groups of three, while keeping the work integrated across the full project. It separates work that each person should complete for learning from shared infrastructure that should be completed once, reviewed, merged into dev, and then pulled by everyone.

# At a Glance

| Person | Group | Owns | Format(s) |
| --- | --- | --- | --- |
| Leigh | A | Air Quality | JSON |
| Matt | A | Weather | Parquet |
| Monah | A | Energy | CSV |
| Sloane | B | Occupancy (new) | CSV |
| Vijay | B | Traffic + City Zones + zone mapping/enrichment | CSV |
| Hakeem | B | Shared data-quality/validation module + Financial data (new) | CSV |

⚠ Before Day 2 starts The shared Day 3 notebook has a syntax error that will crash it as soon as Occupancy or Financial data is loaded. Fix this first — see the Action Items table in Section 9.

# 1. Teams & Ownership

| Group | Members | Primary Day 1–2 Data Focus |
| --- | --- | --- |
| Group A | Leigh, Monah, Matt | Leigh – Air Quality; Matt – Weather; Monah – Energy |
| Group B | Sloane, Vijay, Hakeem | Sloane – Occupancy; Vijay – Traffic, City Zones, and zone mapping/enrichment; Hakeem – shared data-quality/validation module, plus Financial data |

These are starting responsibilities, not permanent silos — across Days 3–5, work rotates so every member gains experience beyond their original assignment.

# 2. What Everyone Does vs. What Only One Person Does

| Work Item | Who Does It? | How It Is Shared |
| --- | --- | --- |
| Git clone, branch workflow, local Spark/Jupyter environment | Each person | Each developer needs a working local environment. |
| Read/understand assigned dataset and run exploration | Each person | Results/code are committed on feature branches and merged. |
| Write transformations/analysis for assigned work | Each person | PR → dev; teammates pull dev. |
| generate_data.py and common generation logic | One shared implementation, reviewed by team | Merge once into dev; everyone pulls it. Do not create six competing versions. |
| Docker Compose/common configuration | One shared implementation, reviewed by team | Merge once into dev; everyone pulls. |
| Database schema / table-creation SQL | One shared implementation with team review | Merge once into dev; execute against the shared PostgreSQL instance. |
| Hosted/shared PostgreSQL instance | Set up once | All six (or both groups, depending instructor decision) connect using environment variables/credentials. |
| Database connection helper/config | One shared implementation | Merge once; each person supplies credentials locally via .env/environment variables. |
| Data loading into shared PostgreSQL | Assign one owner per load/table, with a reviewer | Run once per approved load. Others query the same database; do not duplicate-load blindly. |
| Validation of database tables/results | Everyone should participate | Different members validate counts, schemas, nulls, ranges, and sample queries. |
| Final integration/dashboard | Divide components, integrate together | PRs into dev; final integration tested by both groups. |

# 3. Do All Six People Need to Set Up PostgreSQL Right Now?

No. One shared PostgreSQL instance should be provisioned once — the team does not need six separate hosted databases. Each teammate eventually needs the connection info and must be able to connect/query it, but only one person (or a small infrastructure pair) needs to do the initial provisioning.

For Day 2, keep going with Spark exploration against the raw files while one assigned person/pair sets up the shared PostgreSQL connection. Don't block Day 2 work waiting on database setup.

# 4. Day-by-Day Plan

## Day 1 — Environment & Raw Data Foundation (Today)

The team is starting fresh today — nothing below is assumed done yet. This is the actual kickoff day.

- Shared once: Docker/Spark/Jupyter configuration, common folder structure, generator framework — the generator (scripts/generate-data.py) already exists in the repo, so this is mainly reviewing/running it, not building it from scratch.

- Individual: clone repo, pull dev, create/use feature branch, verify Spark/Jupyter works locally.

- Dataset work: inspect source formats and schemas; preserve CSV/JSON/Parquet differences.

- Integration: merge approved shared setup into dev; everyone pulls dev.

## Day 2 — Exploration, Data Quality & Initial Transformations

| Person | Individual Work | Learning Rotation |
| --- | --- | --- |
| Leigh | Air Quality: JSON loading, schema, nulls/duplicates/ranges, temporal pollution analysis. | Reviews Matt's Parquet work. |
| Matt | Weather: Parquet loading, schema, nulls/duplicates/ranges, weather patterns. | Reviews Leigh's JSON work. |
| Monah | Energy: CSV loading, schema, nulls/duplicates/ranges, energy-consumption patterns. | Reviews the shared CSV/loading logic. |
| Sloane | Occupancy: CSV loading, schema, nulls/duplicates/ranges, and occupancy pattern analysis. Completes the occupancy TODOs already stubbed into the shared day2/day3 notebooks. | Validates Hakeem's data-quality module against Occupancy. |
| Vijay | Traffic (reassigned from Sloane): CSV loading, schema, nulls/duplicates/ranges, hourly traffic patterns. Plus City Zones exploration and zone-mapping/enrichment logic that associates sensor coordinates with reference zones. | Tests zone enrichment against Traffic and at least one other sensor dataset. |
| Hakeem | Builds the reusable Spark data-quality/validation module (record counts, nulls, duplicates, numeric summaries, schema/range checks) used across Traffic, Air Quality, Weather, Energy, and Occupancy. New: Financial data exploration and schema/quality checks. Completes the fiscal TODOs already stubbed into the shared day2/day3 notebooks. | Tests the validator against CSV plus at least one JSON/Parquet dataset. |

Shared/one-person work: Hakeem owns the first reusable validation module; Sloane and Vijay review it against their datasets. Coordinate with Group A so the same validation functionality is reused rather than rebuilt. One member can also begin shared PostgreSQL provisioning without stopping the others.

### Day 2 exit criteria

- All seven datasets (Air Quality, Weather, Energy, Traffic, City Zones, Occupancy, and Financial data) load successfully with the correct Spark reader/options.

- Schemas, record counts, missing values, duplicates, and numeric summaries are understood.

- Traffic hourly, Air Quality day-of-week, and initial Occupancy pattern analyses run.

- Reusable code is merged rather than duplicated across branches.

- Shared PostgreSQL setup has an owner and is either established or clearly tracked as an infrastructure task.

- The file-mapping bug in the shared Day 3 notebook is fixed (Section 9) before anyone tries to load Occupancy or Financial data.

## Day 3 — Cleaning, Transformation & Cross-Dataset Work

- Each person performs at least one meaningful Spark transformation: timestamp conversion, derived hour/day/week fields, type cleanup, null handling, range/anomaly handling, or zone mapping.

- Rotate datasets — no one should spend the entire project only on the dataset they started with.

- Group A rotation: Leigh → Weather or Energy; Matt → Air Quality or Energy; Monah → Air Quality or Weather.

- Group B rotation: Sloane (owns Occupancy) rotates onto Traffic or another sensor dataset for a transformation; Vijay (owns Traffic and City Zones) uses zone enrichment on Occupancy or another sensor dataset; Hakeem applies cleaning/transformation logic to a dataset beyond the validation module, including the new Financial data.

- Cross-group integration: use City Zones/reference coordinates to enrich sensor datasets where appropriate, including Occupancy.

- New derived fields required: Sloane adds occupancy_rate (occupied_rooms ÷ available_rooms) for Occupancy; Hakeem adds expense_rate and revenue_rate for Financial data. Both are referenced by the shared Day 3 aggregation code but aren't in the raw generated files — see Section 9.

- Shared utilities (schemas, loaders, validators) are implemented once, reviewed, merged to dev, and pulled by everyone.

- Begin writing processed outputs to data/processed or the project's required target format.

## Day 4 — Shared PostgreSQL, Analytics & Integration

- Shared infrastructure owner confirms the PostgreSQL host, database, user access, and connection method.

- Credentials must NOT be committed to GitHub. Use environment variables/.env and commit only an example/template if needed.

- Table/load ownership now includes the two new datasets: Occupancy (Sloane) and Financial data (Hakeem). One person loads an approved dataset/table; another validates it. Avoid six people loading the same rows.

- Every team member connects to and queries the shared database, so access isn't understood by only one person.

- Rotate SQL work: each person writes or reviews SQL involving data they did not originally own.

- Run integrated analytics that combine datasets where the project requires it; validate row counts and key business questions.

## Day 5 — Dashboard, Testing, Documentation & Final Delivery

- Split dashboard/visualization work by business question, not by original dataset ownership. Occupancy and Financial data insights should be represented alongside the original five datasets.

- Each group tests the other group's output: queries, charts, filters, counts, and assumptions.

- One person coordinates final README/setup instructions, but every member contributes the section for work they understand.

- One person coordinates final integration into dev/main — don't have six people independently making final infrastructure changes.

- Everyone should be able to explain: source formats, Spark ingestion, transformations, PostgreSQL flow, one cross-dataset insight, and how to reproduce/run the project.

# 5. Recommended Ownership Matrix

| Area | Primary Owner | Reviewer / Backup | Merge/Run Strategy |
| --- | --- | --- | --- |
| Air Quality initial exploration | Leigh | Matt or Monah | Feature PR → dev |
| Weather initial exploration | Matt | Leigh or Monah | Feature PR → dev |
| Energy initial exploration | Monah | Leigh or Matt | Feature PR → dev |
| Traffic initial exploration | Vijay | Sloane or Hakeem | Feature PR → dev |
| Occupancy initial exploration | Sloane | Vijay or Hakeem | Feature PR → dev |
| Financial data initial exploration | Hakeem | Sloane or Vijay | Feature PR → dev |
| generate_data.py | Leigh (working version) | At least one teammate | Merge once → everyone pulls |
| Shared Spark helpers | One developer per helper | Another developer | Merge once → everyone pulls |
| Shared PostgreSQL provisioning | 1 infra owner + 1 backup | Team verifies access | Provision once |
| DB schema/table creation | 1–2 developers | Cross-group review | Execute once against shared DB |
| Data loads to PostgreSQL | One owner per table/load | Second person validates | Load once; validate counts |
| Dashboard/final analytics | Split by business question | Cross-group testing | Integrate via dev |
| City Zones + zone enrichment | Vijay | Sloane or Hakeem | Feature PR → dev |
| Shared data-quality/validation module | Hakeem | Sloane + cross-group reviewer | Merge once → everyone pulls |

# 6. Git Workflow for Both Groups

Use dev as the shared integration branch. Individual work happens on feature branches. Shared code is created once, reviewed, merged, and pulled — not recreated by each teammate.

- Start from an updated dev branch.

- Create/switch to a feature branch for the assigned task.

- Commit only the work for that task.

- Push the feature branch and open a PR into dev.

- Have a teammate review the PR.

- Merge into dev after review/testing.

- Everyone who needs the change pulls dev and merges/rebases it into their active feature branch.

# 7. Shared PostgreSQL Rules

- Provision ONE shared PostgreSQL instance unless the instructor explicitly wants separate databases for the two groups.

- Do not commit passwords or full connection strings to GitHub.

- Use the same schema/table definitions for everyone.

- Designate who is allowed to create/drop/reload tables so teammates don't overwrite each other's work.

- All members should eventually test their own connection and run queries, even if they don't all provision the server.

- Use repeatable SQL/scripts for schema creation and loading so the database can be rebuilt if necessary.

# 8. Team Checkpoint / Definition of Done

A task is not finished just because code exists on one laptop. It's finished when the code is committed, reviewed as appropriate, merged into dev, pulled by the people who need it, and the output has been validated. For shared database work, it's finished when the shared instance is reachable and the team can query the expected tables.

# 9. Action Items From the Repo Review

These came from checking the actual repo (scripts/generate-data.py, README.md, Notes.md, day2_stuff.txt, day3_stuff.txt) against this plan, since Occupancy and Financial data were added after those docs were written. Sloane and Hakeem should read this before starting.

| # | Priority | Issue | What To Do |
| --- | --- | --- | --- |
| 1 | 🔴 Blocker | day3_stuff.txt has a syntax error: the file_mappings dict is missing a comma after the occupancy entry, and the fiscal line has a malformed f-string. | Fix before anyone tries to load Occupancy or Financial data in Day 2/3. Also check for the copy/paste bug nearby (fiscal aggregation mislabeled "occupancy_readings"). |
| 2 | 🟠 Needed in Day 3 | occupancy_rate, expense_rate, and revenue_rate are referenced by the shared aggregation code but are not in the raw generated files. | Sloane derives occupancy_rate = occupied_rooms ÷ available_rooms. Hakeem derives expense_rate and revenue_rate. |
| 3 | 🟡 Naming mismatch | README.md / Notes.md describe occupancy.csv and financial_data.csv, hotel_id, fiscal_id, and rooms_available/rooms_occupied. The actual generator and notebooks use occupancy_data.csv and fiscal_data.csv, sensor_id, and available_rooms/occupied_rooms. | Build against what the generator actually outputs. Flag the README/Notes mismatch at the next checkpoint so someone updates the docs. |
| 4 | 🟡 Terminology | "Financial data" is called fiscal everywhere in code (dataset key, filename). | This plan keeps the label "Financial data" for readability — just know fiscal in code means the same thing. |
| 5 | 🟢 Good to know | day2_stuff.txt and day3_stuff.txt already have loading, quality-rule, temporal-analysis, and interaction-feature code stubbed in with # TODO markers for both occupancy and fiscal. | Sloane and Hakeem are largely completing existing TODOs, not writing this from scratch. |
| 6 | 🟢 Good to know | Occupancy and Financial data are both generated from the same City Zones list, and financial revenue is generated to follow the same seasonal pattern as occupancy. | A natural cross-check for Sloane, Hakeem, and Vijay to run together in Day 3. |

## Immediate Next Actions for Day 1 (Today)

The team is starting completely fresh today, so environment setup comes first for everyone — dataset exploration (the old "Day 2" work) starts once each person's local environment is verified, ideally still today or first thing next session.

| Action | Owner |
| --- | --- |
| Clone the repo, pull dev, start the Docker/Spark/Jupyter cluster, and verify Spark UI + database connectivity. Do this before anything else. | Everyone |
| Review and commit/PR the generate_data.py and related notebook changes already in the repo (nothing further to build here — just review, run, and approve). | Leigh |
| Fix the day3_stuff.txt file_mappings syntax error (Action Item #1) before anyone starts Occupancy or Financial work. | Whoever picks it up first |
| Once environment is verified: begin Air Quality, Weather, and Energy exploration in parallel. | Leigh, Matt, Monah |
| Once environment is verified: begin Occupancy exploration (Sloane's only dataset now — Traffic moved to Vijay). | Sloane |
| Once environment is verified: begin Traffic exploration (newly reassigned from Sloane), plus City Zones exploration and zone mapping/enrichment. | Vijay |
| Once environment is verified: begin the shared data-quality/validation module (tested across multiple file types), and now also Financial data exploration. | Hakeem |
| Set up the shared PostgreSQL instance in parallel; everyone else continues their Day 1/2 work without waiting on this. | 1 owner + 1 backup |
| At the first team checkpoint: confirm everyone's environment is working, reusable loaders/validators are shared (no duplicates), and Occupancy and Financial data are on track alongside the original five datasets. | Whole team |

SparkCity • Revised Team Work Plan • September 2026